## meeting actions
Brimpton Parish Council - Action Tracker October 2020
Date of original minute | Minute Ref | Description | Action | Current Status (Ongoing/Completed/Pending) | Latest update
| 69.2/20 | Enborne Way allotment area | Clerk | Ongoing | Sovereign have had the area strimmed but it is still untidy and there is still a large pile of rubbish which is attracting vermin and the gate is broken. Clerk has contacted Sovereign to pass on complaints and the person responsible has come out to look. Discussions are continuing to determine what still needs to be done in the short and longer term.
7/7/2020 | 60.3/20 | The Parish Council agreed to move to electronic banking. | Clerk | Ongoing | Lloyds provide the necessary dual authorisation via electronic banking but are not currently taking new application because of the Coronavirus restrictions
3/12/2019 | 142.3/19 | The white lines at the sides of Wasing Road and Brimpton Lane are faded and need to be refreshed. Clerk to raise as a case on this | Clerk | Ongoing | Clerk has raised two enquiries 179414 and 179413. WBC have confirmed that this work is in the programme of works for this year at the end of Summer or early Autumn.
2019-03-05 | 99/18 | Speeding : address residents concerns | JD | Ongoing | The purchase of a SID shared with other parishes is to be discussed at October meeting.
| 52.2/20 | A resident raised a concern about overgrown hedges/shrubs on footpaths BRIM19 and BRIM9/2 | Clerk | Completed | Clerk has raised enquiry 185338 with West Berkshire Rights of Way team. They will either cut the path or request that the landowner does this themselves. West Berkshire Council have closed the case as resolved.
2020-03-03 | 16/20 | Mr Hicks asked whether the Wasing Medicine festival licence was approved by West Berkshire Council | Clerk | Completed | WBC confirmed that the licence was approved but it is unknown whether the festival will go ahead due to the Coronavirus restrictions.
3/12/2019 | 142.4 | Clerk to report the damage to the wall at Quaking bridge and request an update from West Berkshire Council | Clerk | Completed | Case 178508 raised but issue was already being tracked by WBC. Latest update from WBC "works are programmed to be carried out in late January 2020 due to the congested work schedule of our preferred contractor. I can also confirm the bridge is inspected on a regular basis." Work has been completed
3/12/2019 | 142.4 | Mrs Cowdery reported that there is fly tipping in Back Lane. Clerk to raise a case with West Berkshire Council. | Clerk | Completed | Case raised. Response from WBC "The details have been logged under our reference 7117657 and have been passed to our Waste Services team for investigation/action." Fly tipping cleared.
2019-11-05 | 130.1 | Request for better signage on the route of footpath 12. It was agreed that the Clerk should raise a request with West Berkshire Council for a way marker sign next to one of the kissing gates on the path | Clerk | Completed | Enquiry raised with West Berkshire Council reference:177819 on 11th November. Still waiting for a response. West Berks have indicated that the Rights of Way team are understaffed and there is therefore a backlog of requests. Mrs Cowdery reported that the new signage is now in place.
7/1/2020 | 5.2/20 | Clerk to contact West Berkshire Council to ask what the criteria are for having a centre line and also the criteria for installing cats eyes. Clerk to also ask what the cost of renewing the lines would be and whether the Parish Council could contribute to this cost | Clerk | Completed | West Berkshire responded as follows :- minimum width for a road to have a centre line is 5.5metres (Brimpton Lane is less than this in places). Cats Eyes are not allowed on roads in a 30mph zone. They have indicated that the Parish Council can not contribute to the cost of re-lining but they will be carrying out an assessment of both Wasing Road and Brimpton Lane, with a view to having works carried out the in the new financial year if required
3/12/2019 | 142.3/19 | Potential highway improvements at Able Bridge should be pursued further. Clerk to discuss with West Berkshire Council to determine what is possible. | Clerk | Completed | Issues with flooding at Able Bridge have been fixed (possibly temporarily) by West Berks clearing and fixing the drainage. Clerk now to discuss a longer term solution with West Berkshire Council. A meeting was held with West Berkshire Highways about the road surface and drainage problems they indicated that the roads are assessed all the time but there is only a limited budget to improve the worst roads.
2019-06-04 | 77.1/19 | A resident raised a concern about the trees around the Solar Farm. 21 of the trees have died and a promised copse at the east of the site has not been planted. Clerk to raise the concern with Wasing Estate. | Clerk/JH | Completed | Clerk has contacted Wise Energy who now run the Solar Farm site and they have provided plans for the replanting of hedges/trees to be carried out this winter. They have given a new estimate for completion by 13th March. Mr. Hicks has contacted them to find out how the trees/shrubs will be maintained after planting. The new trees and shrubs have been planted.
2019-11-05 | 128.2 | Mrs. Cowdery raised the issue of dog fouling on the school field and suggested that dogs should not be allowed on the field. Mr. Hicks to contact the school governors and ask for their view on the matter. | JH | Completed | JH has discussed the issue of dog fouling on the school field with the Chairman of the school governors and the Head Teacher. They are monitoring the situation. No further action for Parish Council

## Parish Plan actions
Parish Plan Recommendations
Timescale | Action No. | Parish Plan Section | Recommendation | Priority in Plan | Action Leader | Latest update
Immediate within 3 months | 3 | Household | Lobby WBC and Gigaclear to ensure project is successfully completed | High | JD | ongoing. Remedial works have been carried out during May 2020. JD continues to chase for progress.
Immediate within 3 months | 14 | Building | Request WBC to pay more attention to enforcing planning conditions | Low | MC | Ongoing. MC has provided information on the planning enforcement team at West Berkshire Council and how they work.
Immediate within 3 months | 18 | Landscape (Listed as crime by Steering Group!) | Report to WBC the need for further training for refuse collectors re litter dropped from recycling boxes | Medium | JH | JH spoke with WBC. Any future issues should be reported by residents directly to WBC
Immediate within 3 months | 20 | Crime | Advertise MOD Police Project Servator on PC website | Medium | Clerk | On website under local info/emergency contacts/police.
Immediate within 3 months | 26 | Communications | Provide link to Parish Magazine digital copy from PC website | Low | Clerk | Completed. Link can be found under Local Info/Church Newsletter
Immediate within 3 months | 29 | Local Government | Provide short biographies of parish councillors & WBC councillor on website | Medium | Clerk | Almost complete. Just waiting for biography from Cllr Boeck
Immediate within 3 months | 30 | Local Government | Discuss with WBC how recycling opportunities can be extended | Medium | JH | JH has had a response from WBC regarding the current status of recycling in the district. Clerk has put some of this information on the website under Local Info/Recycling.
Immediate within 3 months | 34 | Landscape | Publish existing rights of way on PC website | High | Clerk | Completed. On website under Village Info/Village Map and also under local info/footpaths
Medium (3mths-1year) | 1 | Household | Publicise bulk buying oil schemes via PC website | Medium | Clerk | There is some good general advice given by ACRE (Action with Communities in Rural England) about oil buying schemes and Connecting Communities Berkshire (CCB) run a scheme that covers Brimpton. Clerk would propose putting general advice on the website rather than publicising any specific scheme.
Medium (3mths-1year) | 2 | Household | Investigate ways to improve mobile reception in the parish | High | PB
Medium (3mths-1year) | 9 | Transport | Carry out more in-depth survey of speeding in the parish and discuss results with WBC | High | JD | SID monitoring was carried out in October. Next step to monitor 40mph zones. Discussions ongoing with neighbouring parishes about purchasing a shared SID so more monitoring can be done more frequently.
Medium (3mths-1year) | 10 | Transport | Review with WBC what can be done to make junctions safer | High | JD | This is the responsibility of West Berkshire Highways department
Medium (3mths-1year) | 11 | Transport | Investigate ways in which the PC can work with WBC and landowners to keep hedges, verges, ditches and road surfaces in good order | Medium | PM | Mr. Main has contacted West Berkshire Council about ways to work with them and landowners to keep hedges, verges etc. in good order. West Berkshire Council have advised that the best way to track issues is to report them via their online reporting tool. This is already done but could be more widely publicised in the parish.
Medium (3mths-1year) | 33 | Landscape | Publicise existing Mount Charity Permits via PC website | High | Clerk | Link to Wasing website with details about Mount Charity Permits put on PC website but no information about where the permitted paths are.
Long Term (more than 1 year) | 5 | Education | Investigate other transport options to and from secondary schools | Medium | MC | MC has investigated options and sent report to councillors. Clerk has put information about the bus to the Kennet School on the website. JH to also advertise the spaces on the bus via the parish mailing list
Long Term (more than 1 year) | 7 | Church | Investigate land for parking to encourage wider use of Church and school in conjunction with Village Hall | Medium | JD
Long Term (more than 1 year) | 8 | Transport | Explore other transport options for the parish by asking WBC to convene a meeting with all transport providers | Medium | PB
Long Term (more than 1 year) | 12 | Building | Support proposals (subject to compliance with planning regulations and the Village Design Statement) to build up to 10 small private houses over 10 years, affordable to first time buyers and people wishing to downsize, primarily through infilling. | Medium | MC
Long Term (more than 1 year) | 13 | Building | Review settlement boundary | Medium | CB | A response to West Berkshire's review of settlement hierarchy, boundary and HELAA was agreed and sent to West Berkshire's planning policy team. The aim is to setup a working group of residents to review the settlement boundary but this is on hold at the moment due to the coronavirus restrictions..
Long Term (more than 1 year) | 32 | Landscape | Review public rights of way in the parish and look to expand network of footpaths and cycle paths via discussions with local major landowners | High | PM
Ongoing | 4 | Personal | Discuss with parishioners what would make people feel more part of the community | Low | JH
Ongoing | 15 | Health | Promote Good Neighbour scheme | Low | JH
Ongoing | 16 | Crime | Encourage residents to be more vigilant towards fly tipping and litter | High | JH | Ongoing
Ongoing | 17 | Crime | Campaign to make residents more mindful of noise (Link to WBC website) | Medium | Clerk | A link has been added to the PC website under local info to link to the WBC page on noise. Complete
Ongoing | 19 | Crime | Continue with community litter picking events | Medium | JH | Litter pick arranged for 28th March - Unfortunately the litter pick has been cancelled due to the Coronavirus restrictions.
Ongoing | 25 | Communications | Encourage parishioners to sign up for Update email on PC website and Facebook page | Low | Clerk | ongoing
Ongoing | 27 | Communications | More publicity of PC website and Facebook page | Medium | Clerk | ongoing
Ongoing | 28 | Local Government | Develop closer working relationship with District Councillor | Medium | JH | ongoing
Ongoing | 35 | Landscape | Continue to oppose gravel extraction plans | High | JH | Manor Farm and Boot Farm have been removed from West Berkshire's Mineral and waste plan.
No Action | 6 | Church | PCC to investigate other uses for the Church and promote events. | Refer to PCC | None
No Action | 21 | Crime | Pursue Neighbourhood Watch in village and Hyde End | Refer to NW | None
No Action | 22 | Facilities | Investigate feasibility of ideas for Village Hall | Refer to VHC | None
No Action | 23 | Facilities | Review suggestions for Recreation Ground | Refer to RGT | None
No Action | 24 | Facilities | Encourage better promotion of events held at the Village Hall | Refer to VHC | None
No Action | 31 | Landscape | Organise a local workforce. | Low | None

## Old completed actions 2019
Date of original minute | Minute Ref | Description | Action | Current Status (Ongoing/Completed/Pending) | Latest update
2019-12-03 | 144/19 | NALC consultation on strengthening police powers to deal with unauthorised encampments. | PM/Clerk | Completed | Response drafted by PM and Clerk sent to NALC
2019-11-05 | 135.2 | There is a booklet called ‘Are you ready ?’ with advice for households on how to plan for and deal with emergencies. Clerk to add a link to the booklet to the Parish Council website. | Clerk | Completed | Clerk added a link on the Emergency Contacts page of the website.
2019-11-05 | 130.3 | Mr. Dolphin agreed to check the grit bins in the village and let the Clerk know if they need refilling. Clerk to check bin in Hyde End Lane. It was reported that the hedge needs to be cut over the grit bin which is located by the monument. | Clerk/JD | Completed | Grit bins have been refilled.
2019-10-01 | 124.2/19 | Mr. Dolphin asked whether a page could be added to the Parish Council website to list local businesses. Clerk to investigate the legalities of this and find out whether other Parish Councils provide this information on their website. | Clerk | Completed | Clerk has found that some parish/town councils do provide this service. HALC have advised that there is nothing preventing a parish council from doing this but advised that it might be better to link to an existing directory. The PC would be responsible for ensuring the quality and accuracy of the data in the directory and ensuring it meets GDPR requirements. The decision was made at the November meeting not to pursue this any further.
2019-10-01 | 124.1/19 | Hedges along the footpath from Bannister Place to the school are overgrown. This is not an official footpath but Mr. Dolphin will report the West Berkshire Council in the first instance. | JD | Completed | West berkshire have responded to say that the path is not an adopted public highway and they cannot therefore request for the hedges to be cut back.
2019-06-04 | 74/19 | VE day 75 celebrations | JH | Completed | JH has reported back to council.
2019-02-05 | 12/19 | Drain outside pub needs to be cleared and gulleys along Wasing Road | Clerk/JH | Completed | West Berkshire Council have fixed and drain appears to be working.
2019-06-04 | 77.2/19 | Concern about garden waste refuse collectors leaving bins at the end of Church Road instead of returning them to outside residents’ homes. | JH | Completed | JH has contacted West Berkshire Council twice and they have spoken to their contractors. If the issue of bins not being returned happens again residents should report this directly to West Berkshire Council.
2019-06-04 | 77.3/19 | Concern raised about a new gateway which has been installed on to the Brimpton Common byway by the Wasing Estate. | Clerk/JH | Completed | West Berkshire planning department have been out to site but the outcome of this visit is unknown. Wasing maintain that no planning permission was needed for a gateway on to their own land. Still ongoing but not a parish council matter so set to completed.
4/6/2019 | 69.2/19 | 69.2 School Railings. The School governors are due to meet on 18th July and Mr. Hicks will ask for an update on the replacement railings at this meeting. | JH | Completed | School railings have now been replaced and road markings repainted.
2019-08-06 | 95.3/19 | Thames Water recently dug up the triangle of land at the junction of Station Road and Wasing Road but have not reinstated it to a good standard. The finger post has also been removed. Clerk to report to West Berkshire Council. | Clerk | Completed | Clerk raised case with West Berks ref: 175111. Triangle of land has been improved and finger post returned.
2019-05-07 | 56/19 | Tree fallen down on footpath 6. | Clerk | Completed | Tree has been cleared from the footpath
2019-05-07 | 59/19 | Clerk to ensure that policies are updated and up to date versions uploaded to the website | Clerk | Completed | Standing orders and financial regulations have been updated.
2019-03-05 | 32.4/19 | 40mph reminder roundel on Brimpton Road fallen off | Clerk | Completed | 40mph roundel has now been replaced.
2019-03-05 | 32.3/19 | Dog fouling | Clerk/JH | Completed | Raise awareness via email and facebook. Put up signs on churchyard footpath. Clerk has put signs up at the start of the footpath into the fields
2019-02-05 | 125/18.1 | Clerk to chase West Berkshire for an update on the installation of road signs in Blacknest Lane. | Clerk | Completed | Signs now in place
| 18/19 | Purchase of memorial bench | Clerk | Completed | Bench now installed. PC to put on asset register and insure
2018-10-30 | 19/19 | Purchase of a wifi enabled projector | clerk/pb | Completed | Equipment ordered and given to Phil/John for installation
2018-09-04 | 132/18 | Investigate installation of mirror at end of Enborne Way | DB | Completed | Cllr Boeck has confirmed that WBC do not support the installation of mirrors
| 100/18.4 | Replacement of school railings to improve visibility | JH | Completed | AWE have approved a grant of £2000 to the school for them to complete the work to the railings and road markings.
2018-09-04 | 100/18.5 | Overgrown shrubs outside postoffice | Clerk/JH | Completed | A resident has cut back the shrubs so no longer an issue
2019-01-08 | 12/19.0 | Ask Planning enforcement about the crossing at the Grundon site | Clerk/DB | Completed | The road has been reinstated
2/7/2019 | 83.3/19 | Mrs Cowdery raised a concern that although there is a dropped kerb at the end of Enborne Way there is no corresponding dropped kerb at the other side of Brimpton Lane. It would therefore be very difficult to cross the road with a wheel chair or pram. Clerk to raise a case with West Berkshire Highways department. | Clerk | Completed | Clerk raised an enquiry with West Berkshire and they responded saying that the existence of a telecommunications chamber in the footway along Brimpton Lane prevents a dropped kerb being installed opposite the existing dropped kerbs to the north of Enborne Way. They also believe it would be more dangerous for pedestrians if the kerb was dropped.
2019-08-06 | 95.2/19 | Gigaclear installation of cables in Church Lane and Hatch Lane | JH | Completed | Gigaclear have indicated that they will not be installing cables in Hatch Lane.
2019-08-06 | 95/19 | Footpath 15 which is on the Fuel Allotment is blocked by a fallen tree and overhanging branches but this has not been cleared. | Clerk | Completed | Clerk has raised twice with West Berks due to safety concerns. Ref: 174891 and 175165. Update on 1st Aug was that they would inspect and deal with within 3 weeks. Has now been done.
2019-05-07 | 43/19 | Some road signs in the parish are obscured by overgrown hedges/shrubs. | JH | Completed | Clerk has raised cases including for the Blacknest Lane sign. It appears that some of the signs have been cleared but not sure if this was done by residents or West Berks.